## Fall
GANTT CHART | [24 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | Predicting Flight Arrival Delays: Machine Learning Approaches
[5 empty] | PHASE ONE | [6 empty] | PHASE TWO | [41 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08
[5 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Project Proposal
Introduction & Background | Richie | 2025-09-28 | 2025-10-02 | 4 | bar: 2025-09-29 M to 2025-09-29 R
Problem Definition | Antonio | 2025-09-28 | 2025-10-02 | 4 | bar: 2025-09-29 M to 2025-09-29 R
Methods | Sara, Magnus | 2025-09-28 | 2025-10-02 | 4 | bar: 2025-09-29 M to 2025-09-29 R
Potential Results & Discussion | Richie, Luoyi | 2025-09-28 | 2025-10-02 | 4 | bar: 2025-09-29 M to 2025-09-29 R
Video Recording | All | 2025-09-28 | 2025-10-02 | 4 | bar: 2025-09-29 M to 2025-09-29 R
GitHub Page | Luoyi, Richie | 2025-09-27 | 2025-10-02 | 5 | bar: 2025-09-29 M to 2025-09-29 R
Model 1
Data Sourcing and Cleaning | Richie, Luoyi, Antonio | 2025-10-07 | 2025-10-12 | 5 | bar: 2025-10-06 T to 2025-10-06 U
Model Selection | Magnus, Sara | 2025-10-07 | 2025-10-12 | 5 | bar: 2025-10-06 T to 2025-10-06 U
Data Pre-Processing | Richie, Luoyi, Antonio | 2025-10-12 | 2025-10-15 | 3 | bar: 2025-10-06 S to 2025-10-13 W
Model Coding | Magnus, Sara | 2025-10-15 | 2025-10-17 | 2 | bar: 2025-10-13 W to 2025-10-13 F
Results Evaluation and Analysis | Magnus, Richie, Luoyi | 2025-10-17 | 2025-10-18 | 1 | bar: 2025-10-13 F to 2025-10-13 S
Midterm Report | All | 2025-10-07 | 2025-10-18 | 11 | bar: 2025-10-06 T to 2025-10-13 S
Model 2
Data Sourcing and Cleaning | Magnus, Sara | 2025-10-18 | 2025-10-23 | 5 | bar: 2025-10-13 S to 2025-10-20 W
Model Selection | Richie, Luoyi, Antonio | 2025-10-18 | 2025-10-23 | 5 | bar: 2025-10-13 S to 2025-10-20 W
Data Pre-Processing | Magnus, Sara | 2025-10-23 | 2025-10-26 | 3 | bar: 2025-10-20 W to 2025-10-20 S
Model Coding | Richie, Luoyi, Antonio | 2025-10-26 | 2025-10-28 | 2 | bar: 2025-10-20 S to 2025-10-27 M
Results Evaluation and Analysis | All | 2025-10-28 | 2025-10-31 | 3 | bar: 2025-10-27 M to 2025-10-27 R
Model 3
Data Sourcing and Cleaning | Magnus, Richie, Antonio | 2025-11-01 | 2025-11-05 | 4 | bar: 2025-10-27 F to 2025-11-03 T
Model Selection | Luoyi, Sara, Antonio | 2025-11-02 | 2025-11-07 | 5 | bar: 2025-10-27 S to 2025-11-03 R
Data Pre-Processing | Magnus, Richie, Antonio | 2025-11-05 | 2025-11-09 | 4 | bar: 2025-11-03 T to 2025-11-03 S
Model Coding | Luoyi, Sara, Antonio | 2025-11-09 | 2025-11-12 | 3 | bar: 2025-11-03 S to 2025-11-10 T
Results Evaluation and Analysis | All | 2025-11-12 | 2025-11-13 | 1 | bar: 2025-11-10 T to 2025-11-10 W
Evaluation
Model Comparison | Richie, Luoyi, Sara | 2025-11-13 | 2025-11-23 | 10 | bar: 2025-11-10 R to 2025-11-17 S
Presentation | Antonio, Sara, Magnus | 2025-11-23 | 2025-12-01 | 8 | bar: 2025-11-17 S to 2025-12-01 M
Recording | All | 2025-12-01 | 2025-12-02 | 1 | bar: 2025-12-01 M to 2025-12-01 T
Final Report | All | 2025-11-24 | 2025-12-02 | 8 | bar: 2025-11-24 M to 2025-12-01 T
Formulas:
PHASE TWO = [PHASE ONE]+7

## Fall Overview
GANTT CHART | [7 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | Flight Arrival Delay Prediction
[5 empty] | PHASE ONE | PHASE TWO | [6 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2025-09-29 | 2025-10-06 | 2025-10-13 |  | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08
Project Proposal |  | 2025-09-28 | 2025-10-03 | 5
Introduction & Background | Karishma | 2021-09-27 | 2021-10-04 | 7
Problem Definition | Tim | 2021-09-27 | 2021-10-04 | 7
Methods | Bryan | 2021-09-27 | 2021-10-04 | 7
Potential Results & Discussion | Noah & Gabby | 2021-09-27 | 2021-10-04 | 7
Video Recording | All | 2021-10-04 | 2021-10-07 | 3
GitHub Page | Karishma | 2021-10-04 | 2021-10-07 | 3
Model 1 |  | 2025-10-06 | 2025-10-18 | 12
Data Sourcing and Cleaning | Tim | 2021-10-07 | 2021-10-15 | 8
Model Selection | Karishma | 2021-10-15 | 2021-10-18 | 3
Data Pre-Processing | Tim | 2021-10-18 | 2021-10-25 | 7
Model Coding | Karishma | 2021-10-25 | 2021-11-08 | 13
Results Evaluation and Analysis | Tim | 2021-11-08 | 2021-11-16 | 8
Midterm Report | All | 2021-11-08 | 2021-11-16 | 8
Model 2 |  | 2025-10-19 | 2025-10-31 | 12
Data Sourcing and Cleaning | Gabby | 2021-10-18 | 2021-10-22 | 4
Model Selection | Noah | 2021-10-22 | 2021-10-25 | 3
Data Pre-Processing | Gabby | 2021-10-25 | 2021-10-29 | 4
Model Coding | Noah | 2021-10-25 | 2021-11-19 | 24
Results Evaluation and Analysis | Gabby | 2021-11-19 | 2021-11-24 | 5
Model 3 |  | 2025-11-01 | 2025-11-13 | 12
Data Sourcing and Cleaning | Bryan | 2021-10-18 | 2021-10-22 | 4
Model Selection | Bryan | 2021-10-22 | 2021-10-25 | 3
Data Pre-Processing | Bryan | 2021-10-25 | 2021-10-29 | 4
Model Coding | Bryan | 2021-10-25 | 2021-11-19 | 24
Results Evaluation and Analysis | Bryan | 2021-11-19 | 2021-11-24 | 5
Evaluation |  | 2025-11-14 | 2025-12-02 | 18
Model Comparison | Tim | 2021-11-29 | 2021-12-07 | 8
Presentation | All | 2021-11-29 | 2021-12-06 | 7
Recording | All | 2021-12-06 | 2021-12-07 | 1
Final Report | All | 2021-11-29 | 2021-12-07 | 8
Formulas:
PHASE TWO = [PHASE ONE]+7